## Andrew Stamps (User Stories)
TASK | STATUS | ASSIGNED TO
BL-100 (Small) Define global bank structure | COMPLETED | Andrew Stamps
BL-200 (Small) User input of items and validation | COMPLETED | Andrew Stamps
BL-300 (Small) User input of funds and validation | COMPLETED | Andrew Stamps
BL-400 (Small) Calculate Change | COMPLETED | Andrew Stamps
BL-500 (Small) Display Item Total | COMPLETED | Andrew Stamps
BL-600 (Medium) Check if enough funds are in bank | COMPLETED | Andrew Stamps
BL-650 (Medium) Dispense Change | COMPLETED | Andrew Stamps
BL-650 (Medium) Dispense Change | COMPLETED | Andrew Stamps
BL- 700 (Small) validate credit card vendor
STANDUP @ 10:15 AM

## Caitlin Glenn
TASK | STATUS | ASSIGNED TO
BL-100 (Small) Define global bank structure | COMPLETE | Caitlin Glenn
BL-200 (Small) User input of items and validation | IN PROGRESS | Caitlin Glenn
BL-300 (Small) User input of funds and validation | COMPLETE | Caitlin Glenn
BL-400 (Small) Calculate Change | COMPLETE | Caitlin Glenn
BL-500 (Small) Display Item Total | COMPLETE | Caitlin Glenn
BL-600 (Medium) Check if enough funds are in bank | COMPLETE | Caitlin Glenn
BL-650 (Medium) Dispense Change | COMPLETE | Caitlin Glenn
BL-650 (Medium) Dispense Change | NOT STARTED | Caitlin Glenn

## Kenny Tran
WEEK 1
DATE STARTED | TASK | DATE COMPLETED | NOTES | STATUS | ASSIGNED TO
2021-10-25 | BL-50 (Small) Build Sprint Plan | 2021-10-25 | Learned to build sprints and apply structs to create new datatypes. Few questions about utilizing structs, but everything was understable. | COMPLETED | Kenny Tran
2021-10-26 | BL-100 (Small) Define global bank structure | 2021-10-26 | Created a struct to define physical currency in the kiosk. Tested whether it was better to do a physical count of each coin and bill or assign currency values to each. The first option was ideal for my approach. | COMPLETED | Kenny Tran
2021-10-27 | BL-200 (Small) User input of items and validation | 2021-10-27 | Created functions for general string input. Researched into greedy algorithms. | COMPLETED | Kenny Tran
2021-10-28 | BL-300 (Small) User input of funds and validation | 2021-10-29 | n/a | COMPLETED | Kenny Tran
2021-10-29 | BL-400 (Small) Calculate Change | 2021-10-29 | n/a | COMPLETED | Kenny Tran
2021-10-27 | BL-500 (Small) Display Item Total | 2021-10-28 | n/a | COMPLETED | Kenny Tran
2021-10-29 | BL-600 (Medium) Check if enough funds are in bank | 2021-10-31 | Tested multiple ways to store default cash with customer payment as an increment to the money supply and decrement when returning change/refund. | COMPLETED | Kenny Tran
2021-10-29 | BL-700 (Medium) Dispense Change | 2021-10-31 | Tested different ways to implement both change and refunds in the case of a cancelled transaction. Sequential placement of syntax was a big step to finding the solution. | COMPLETED | Kenny Tran
2021-10-29 | BL-800 (Medium) Assemble functions into complete project | 2021-10-31 | Refer to Nov 1 | COMPLETED | Kenny Tran
2021-10-30 | REVIEW AND CLEAN CODE (OUT OF OFFICE) | 2021-10-30 | n/a | COMPLETED | Kenny Tran
2021-10-31 | REVIEW AND CLEAN CODE (OUT OF OFFICE) | 2021-10-31 | n/a | COMPLETED | Kenny Tran
2021-11-01 | BL-900 (Medium) Code Review | 2021-11-01 | Readjustments were implemented based on given feedback. Continuing to fine tune "COMPLETED" sections as making further additions to the project. | COMPLETED | Kenny Tran
WEEK 2
DATE STARTED | TASK | DATE COMPLETED | NOTES | STATUS | ASSIGNED TO
2021-11-02 | BL-1000 (Small) Create payment option menu (cash or credit) | 2021-11-02 | n/a | COMPLETED | Kenny Tran
2021-11-03 | BL-1100 (Medium) Allow split payment options | 2021-11-08 | 11/7/21 Working to link both cash and card payment | COMPLETED | Kenny Tran
2021-11-03 | BL-1200 (Large) Validate CC Vendor (research) | 2021-11-06 | 11/3/21 Researching Vendor Identification - Regular Expressions (Regex) may be the best solution to solving vendor validation. Further research needed. 11/4/21 Using array approach to finding credit card vendors. Solving and testing is still the works. 11/5/21 Tested array approach. Results were successful. Continuous testing will occur as new additions are made to the program. | COMPLETED | Kenny Tran
2021-11-02 | BL-1000 (Large) Validate card numbers (research) | 2021-11-05 | 11/2/21: Researched Luhn Algorithm/Mod 10 and have begun implementing it into a function to validate card payments. (Research completed) 11/3/21: Further testing needed. | COMPLETED | Kenny Tran
2021-11-05 | BL-1100 (Medium) Credit Fail Prompt/Switch Payment option ie using another credit card or pay cash (ask more questions) | 2021-11-07 | n/a | COMPLETED | Kenny Tran
2021-11-05 | BL-1200 (Medium) Create cashback prompt | 2021-11-07 | n/a | COMPLETED | Kenny Tran
2021-11-05 | BL-1300 (Medium) Reimburse change | 2021-11-07 | n/a | COMPLETED | Kenny Tran
2021-11-08 | BL-1350 (Medium) Polish project/feedback | 2021-11-08 | 11/8/21 Cleaned code and added "bells and whistles" to program | COMPLETED | Kenny Tran
2021-11-16 | BL-1400 (Large) Evaluations for Kiosk project and Personal Project |  | n/a | COMPLETED | Kenny Tran

## Nhut Luong
2021-10-25 | Create VS Project | Design User Defined Data Structure | TASK | STATUS | ASSIGNED TO
2021-10-26 |  |  | BL-100 (Small) Define global bank structure | COMPLETED | Nhut Luong
2021-10-27 |  |  | BL-200 (Small) User input of items and validation | COMPLETED | Nhut Luong
2021-10-28 |  |  | BL-300 (Small) User input of funds and validation | COMPLETED | Nhut Luong
2021-10-29 |  |  | BL-400 (Small) Calculate Change | COMPLETED | Nhut Luong
|  |  | BL-500 (Small) Display Item Total | COMPLETED | Nhut Luong
|  |  | BL-600 (Medium) Check if enough funds are in bank | COMPLETED | Nhut Luong
2021-11-01 |  |  | BL-650 (Medium) Dispense Change | COMPLETED | Nhut Luong
2021-11-02 |  |  | BL-700 (Medium) Assemble functions into complete project | COMPLETED | Nhut Luong
2021-11-03
2021-11-04 |  |  | BL - 700 (SMALL) User input for credit card or cash payment | COMPLETED
2021-11-05 |  |  | BL- 750 (SMALL) validate credit card vendor | COMPLETED
|  |  | BL - 800 (SMALL) Validate card number | COMPLETED
|  |  | BL - 850 (SMALL) Add money request function | COMPLETED
2021-11-08 |  |  | BL - 900 (SMALL) Add change payment function | IN PROGRESS
2021-11-09 |  |  | BL - 950 (SMALL) Allow user to pay remaining balance in cash | NOT STARTED
2021-11-10
2021-11-11

## Alex Cruz
Date | Daily Project Goals |  |  |  | TASK | STATUS | ASSIGNMENT
2021-10-25 | Project Plan | Create VS Project | User Defined Functions(1a)
2021-10-26 | Input(1b) | Input Validation (1c) | Determin Total (1d) |  | BL-100 (Small) Define global bank structure | COMPLETED | Alex Cruz
2021-10-27 | Get Payment Loop(2a) | Show remaining Cash Due (2b) | Output Change Due to user (3b) |  | BL-200 (Small) User input of items and validation | COMPLETED | Alex Cruz
2021-10-28 | Validate Currency Input (2c) | Validate Kiosk has enough money (3a) | Return Change to user (3c) | Alt Payment Methods (3d) | BL-300 (Small) User input of funds and validation | COMPLETED | Alex Cruz
2021-10-29 | Assembling Functions | Testing |  |  | BL-400 (Small) Calculate Change | COMPLETED | Alex Cruz
[5 empty] | BL-500 (Small) Display Item Total | COMPLETED | Alex Cruz
[5 empty] | BL-600 (Medium) Check if enough funds are in bank | COMPLETED | Alex Cruz
2021-11-01 | payment menu |  |  |  | BL-650 (Medium) Dispense Change | COMPLETED | Alex Cruz
2021-11-02 | id and display card vendor | validate card number |  |  | BL-700 (Medium) Assemble functions into complete project | COMPLETED | Alex Cruz
2021-11-03 | cashback | Spliting Bill Option
2021-11-04 |  |  |  |  | BL-800 (Small) Payment Menu | COMPLETED | Alex Cruz
2021-11-05 |  |  |  | Missed Standup 10/27 | BL-900 (Small) ID Card Vendor | COMPLETED | Alex Cruz
[5 empty] | BL-1000 (Medium) Validate Card Number | COMPLETED | Alex Cruz
[5 empty] | BL-1100 (Small) Additional Payment Option | COMPLETED | Alex Cruz
2021-11-08 | presentations |  |  |  | BL-1200 (Medium) Cash Back | COMPLETED | Alex Cruz
2021-11-09 | presentations
2021-11-10
2021-11-11

## Rory Wren
| COMPLETE | RORY WREn | BL-100 (Small) Define global bank structure
BL-200 (Small) User input of items and validation | COMPLETE | ROry WRen
BL-300 (Small) User input of funds and validation | COMPLETE | RORY WREN
BL-400 (Small) Calculate Change | COMPLETE | Andrew Stamps
BL-500 (Small) Display Item Total | COMPLETE | RORY WREN
BL-600 (Medium) Check if enough funds are in bank | NOT STARTED | Andrew Stamps
BL-650 (Medium) Dispense Change | COMPLETE | RORY WREN
BL-700 (Medium) Assemble functions into complete project | COMPLETE | RORY WREN
Missed Standup 10/27

## zach
2021-10-25 |  | progress
2021-10-26 | TASK
| BL-500 (Small) Display Item Total | completed
2021-10-27 | BL-100 (Small) Define global bank structure | completed
2021-10-28 | BL-200 (Small) User input of items and validation | completed
2021-10-29 | BL-300 (Small) User input of funds and validation | completed
| BL-400 (Small) Calculate Change | completed
2021-11-01 | BL-600 (Medium) Check if enough funds are in bank | completed
2021-11-02 | BL-650 (Medium) Dispense Change | completed
2021-11-03 | BL-700 (Medium) Assemble functions into complete project | completed
2021-11-04
2021-11-05
2021-11-08 | add card functionality and validation | working,
2021-11-09 | add cashback functionality | working
2021-11-10 | add cash and card payment option | not started
2021-11-11

## David Lamb
TASK | STATUS
BL-100 (Small) Define global bank structure | COMPLETED
BL-200 (Small) User input of items and validation | COMPLETED
BL-300 (Small) User input of funds and validation | COMPLETED
BL-400 (Small) Calculate Change | COMPLETED
BL-500 (Small) Display Item Total | COMPLETED
BL-600 (Medium) Check if enough funds are in bank | COMPLETED
BL-650 (Medium) Dispense Change | COMPLETED
BL-700 (Small) Make prompts for user for to pay with cash or card | COMPLETED
BL- 800 (Small) validate users credit card vendor | COMPLETED
BL-900(small) validate user credit card number | COMPLETED
BL-1000(Medium) display amount paid with card and pay rest with cash | INPROGRESS
BL-1050(Medium) if tranaction fails ask for another form of payment | NOT STARTED

## Noah Gill
TASK | STATUS
BL-100 (Small) Define global bank structure | FINISHED
BL-200 (Small) User input of items and validation | FINISHED
BL-300 (Small) User input of funds and validation | FINISHED
BL-400 (Small) Calculate Change | FINISHED
BL-500 (Small) Display Item Total | FINISHED
BL-600 (Medium) Check if enough funds are in bank | FINISHED
BL-650 (Medium) Dispense Change | FINISHED
BL-700 (Medium) Assemble functions | FINISHED
Kiosk Part 2 | FINISHED
Testing | FiNISHED
Formatting, commenting, & cleaning up | IN PROGRESS
Adding more thorough card checks (current one works but can be bypassed) | IN PROGRESS

## Karlyle McClendon
2021-10-25 | TASK | STATUS | ASSIGNED TO
2021-10-26 | BL-100 (Small) Define global bank structure | COMPLETE | Karlyle McClendon
2021-10-27 | BL-200 (Small) User input of items and validation | COMPLETE | Karlyle McClendon
2021-10-28 | BL-300 (Small) User input of funds and validation | COMPLETE | Karlyle McClendon
2021-10-29 | BL-400 (Small) Calculate Change | COMPLETE | Karlyle McClendon
2021-10-30 | BL-500 (Small) Display Item Total | COMPLETE | Karlyle McClendon
2021-10-31 | BL-600 (Medium) Check if enough funds are in bank | COMPLETE | Karlyle McClendon
2021-11-01 | BL-650 (Medium) Dispense Change | COMPLETE | Karlyle McClendon
2021-11-02 | BL-700 (Medium) Assemble functions into complete project | IN PROGRESS | Karlyle McClendon
2021-11-03
2021-11-04 | BL-800(Small) User input of Credit Card vendor and validation | COMPLETE | Karlyle McClendon
2021-11-05 | BL-900(Small) User input of credit card number & validation | COMPLETE | Karlyle McClendon
2021-11-06 | BL-950(Small) Input function for requesting money | IN PROGRESS | Karlyle McClendon
2021-11-07 | BL-1000(Small) Cashback input and function | IN PROGRESS | Karlyle McClendon
2021-11-08 | BL-1050(Input user to recieve another form of payment if there is a transaction failure) | IN PROGRESS | Karlyle McClendon
2021-11-09 | BL - 1100 (Small)User has choice whether to use card or cash for payment | IN PROGRESS | Karlyle McClendon
2021-11-10 | BL - 1150 (Small) Assemble functions into complete project | NOT STARTED
2021-11-11

## Kobe Pavlus
2021-10-25 | start vs project
2021-10-26
2021-10-27
2021-10-28
2021-10-29
2021-11-01
2021-11-02
2021-11-03
2021-11-04
2021-11-05
2021-11-08
2021-11-09
2021-11-10
2021-11-11
2021-11-12
Missed Standup 10/27

## Kevin Wilson
TASK | STATUS | ASSIGNED TO
BL-100 (Small) Define global bank structure | Completed | Kevin Wilson
BL-200 (Small) User input of items and validation | Completed | Kevin Wilson
BL-300 (Small) User input of funds and validation | Completed | Kevin Wilson
BL-400 (Small) Calculate Change | Completed | Kevin Wilson
BL-500 (Small) Display Item Total | Completed | Kevin Wilson
BL-600 (Medium) Check if enough funds are in bank | Completed | Kevin Wilson
BL-650 (Medium) Dispense Change | Completed | Kevin Wilson
BL-700 (Medium) Assemble functions into complete project | In Progress | Kevin Wilson
BL 750 (Small) Create Payment Selection Menu | Completed | Kevin Wilson
BL 800 (Small) Validate and Display Card type | Completed | Kevin Wilson
BL 850 (Medium) Charge Card (using bank transaction function) | In Progress | Kevin Wilson
BL900 (Medium) Work on offering cash back option | Completed | Kevin Wilson
BL950(Medim) Offering other payment options if transaction fails | Not Started | Kevin Wilson
BL000(Smedium)Cleaning everything up and Making sure it's functioning properly | Not Started | Kevin Wilson

## Daniel Spiering
2021-10-25 | TASK | STATUS | ASSIGNED TO
2021-10-26 | BL-100 (Small) Define global bank structure | Finished | Daniel Spiering
2021-10-27 | BL-200 (Small) User input of items and validation | Finished | Daniel Spiering
2021-10-28 | BL-300 (Small) User input of funds and validation | Finished | Daniel Spiering
2021-10-29 | BL-400 (Small) Calculate Change | Finished | Daniel Spiering
| BL-500 (Small) Display Item Total | Finished | Daniel Spiering
| BL-600 (Medium) Check if enough funds are in bank | Finished | Daniel Spiering
2021-11-01 | BL-650 (Medium) Dispense Change | Finished | Daniel Spiering
2021-11-02 | BL-700 (Medium) Assemble functions into complete project | Finished | Daniel Spiering
2021-11-03
2021-11-04 | BL-800 implement menu to pick a payment option | Finished
2021-11-05 | BL-900 allow to break up payment types | Finished
| BL-1000 prompt for card number | Finished
| BL-1100 validate card number and vendor | Finished
2021-11-08 | BL-1200 ask if customer wants cash back | Finished
2021-11-09 | BL-1300 dispense cash back | Finished
2021-11-10 | BL-1400 further testing and clean up | in progress
2021-11-11

## Veto F Roley
Date | Create VS Project | Design User defined data structured | Task | Status | Started | Projected Start/Complete | Completed
2021-10-25 |  |  | Do Project Outline | Completed | 2021-10-25 | Complete | 2021-10-25
2021-10-26 |  |  | Determine possible payment methods | Completed | 2021-10-25 | Complete | 2021-10-25
2021-10-27 |  |  | Determine bills/coins in circulation | Completed | 2021-10-25 | Complete | 2021-10-25
2021-10-28 |  |  | Ensure understanding of data types | In Progress | 2021-10-25 | 2021-10-27
2021-10-29 |  |  | Create engine to track cash input/output | Not Started |  | 2021-10-26
2021-10-30 |  |  | Create engine to track and display bills and cash left in machine | Not Started |  | 2021-10-26
2021-10-31 |  |  | Create user input engine for cost | Not Started |  | 2021-10-28
2021-11-01 |  |  | Research "greedy" algorithm | Not Started |  | 2021-10-28
2021-11-02 |  |  | Develop engine to efficiently pay change to the customer | Not Started |  | 2021-10-28
2021-11-03 |  |  | Develop engine to end current transaction and start new transact | Not Started |  | 2021-10-28
2021-11-04
2021-11-05 |  |  | Missed Standup 10/27
2021-11-06
2021-11-07
2021-11-08
2021-11-09
2021-11-10
2021-11-11

## Carrie Curtis
DATE | TASK | STATUS | ASSIGNED TO
2021-10-27 | BL-100 (Small) Define global bank structure | COMPLETED | Carrie Curtis
| BL-200 (Small) User input of items and validation | COMPLETED | Carrie Curtis
| BL-300 (Small) User input of funds and validation | NOT STARTED | Carrie Curtis
| BL-400 (Small) Calculate Change | NOT STARTED | Carrie Curtis
| BL-500 (Small) Display Item Total | NOT STARTED | Carrie Curtis
| BL-600 (Medium) Check if enough funds are in bank | IN PROGRESS | Carrie Curtis
| BL-650 (Medium) Dispense Change | NOT STARTED | Carrie Curtis

## Jose Arias
WK | TASK | STATUS | ASSIGNED TO
WEEK 1 | BL-100 (Small) Define global bank structure | COMPLETE | Jose Arias
| BL-200 (Small) User input of items and validation | COMPLETE | Jose Arias
| BL-300 (Small) User input of funds and validation | COMPLETE | Jose Arias
| BL-400 (Small) Calculate Change | COMPLETE | Jose Arias
| BL-500 (Small) Display Item Total | COMPLETE | Jose Arias
| BL-600 (Medium) Check if enough funds are in bank | COMPLETE | Jose Arias
| BL-650 (Medium) Dispense Change | COMPLETE | Jose Arias
| BL-700 (Medium) Assemble functions into complete project | COMPLETE | Jose Arias
WK | TASK | STATUS | ASSIGNED TO
WEEK 2 | BL - 700 (Small) validate credit card vendor/research | COMPLETE | Jose Arias
| BL - 750 (Small) user input of credit card & validation | COMPLETE | Jose Arias
| BL - 800 (Small) user input cashback function | COMPLETE | Jose Arias
| BL - 825 (Small) calculate cashback and balance | COMPLETE | Jose Arias
| Bl - 875 (Small) incorporate money request function | COMPLETE | Jose Arias
| BL - 900 (Medium) dispense refund function | COMPLETE | Jose Arias
| BL - 1100 (Medium) incorporate money request func | COMPLETE | Jose Arias
| BL - 1150 (Small) Test/TryBreak/Feedback | COMPLETE | Jose Arias
WK | TASK | STATUS | ASSIGNED TO
WEEK 2 | BL - 2000 (Small) Personal Project - Idea/Concept | COMPLETE | Jose Arias
| BL - 2050 (Small) Personal Project - Outline/Format | In Progress | Jose Arias
| BL - 2100 (Medium) Personal Project - Code Main Body | In Progress | Jose Arias
| BL - 2200(Medium) Personal Project - Code Validation/Functions | In Progress | Jose Arias
| BL - 2000 (Small) Personal Project - Put it All together/Test/TryBreak | In Progress | Jose Arias
| BL - 3000 (Small) Presentation - Outline | COMPLETE | Jose Arias
| BL - 3050 (Medium) Presentation - Powerpoint | In Progress | Jose Arias
| BL - 3100 (Large) Finish Details/Present | In Progress | Jose Arias